## D4-6
Entity Delivery | FL | Module | Feature | Delivery | Release | BRDs | As-is APIs' Start Date | As-is APIs' Finished Date | PIC | Status | Comment | Change Ref | Description | BA & PO in charge | Total: 60 | Open: 31 | WIP: 6 | Done: 18
D1 | 02_07 | Authorization | Forgot password | 1 | D6 | OP00008 - Forgot password.docx | 26.10.2018 | 14.11.2018 | HaNV9 | WIP |  | UIUX.N11 | Duplicate with CR in Portfolio Q4/2018 | TuCV
D5 | 03_01 | Main | My finance | 4 | D4 | My Finance.docx | 01.09.2018 | 09.11.2018 | VanNTH10 | WIP
D1 | 04_10_02 | Card | Supplement Card | 4 | D4R14 | Card030_Supplement card.docx | 07.11.2018 | 13.11.2018 | CongHV | WIP
D5 | 04_13 | Card | Credit open new credit cards | 6 | D6R17 | Card022_Open new credit card.docx | 22.10.2018 | 25.10.2018 | CuongNH25 | Done |  | UIUX.U19 | https://jira.vpbank.com.vn/browse/NEB-1123
| 04_ | Card | Card Installment (Đăng ký vay trả góp) | 4 | D4 | Card024_Card Installment.doc | 22.10.2018 | 26.10.2018 | HiepNQ1 | Done
| 04_ | Card | Payment and installment registration | 4 | D4 | Card024_Card Installment.doc |  |  |  | Open |  |  | Thanh toán và đăng ký trả góp
D1 | 07_07 | Payment | Alert bill pay | 6 | D6 | OP00038_Alert Bill Pay.docx |  |  | BachLD | Open
| 12_03 | Loan | Unsecured personal loan(UPL) | 4 | D4R16 |  | 2018-11-05 | 2018-11-16 | KhoaND | Done |  |  |  | BA: LanNTM (lanntm@vpbank.com.vn, 0386462991) PO: NinhDT5 (ninhdt5@vpbank.com.vn, 0984049609)
D4 | 11_02 | UPL | View detail UPL | 4 | D4R16 | Lend013b_Loan Detail.docx | 2018-11-05 | 2018-11-16 | KhoaND | Done
D4 | 11_01 | UPL | Open UPL | 4 | D4R16 | Lend008_Open UPL.docx | 2018-11-12 | 2018-11-16 | KhoaND | Done
D4 | 09_01 | Saving | Saving info | 4 | D6R17 | Main001_My Finance.doc | 2018-11-12 | 2018-11-16 | Thanh | Done |  |  | (account number, principal amount, terms, interest rate, currency, maturity date, interest date)
D4 | 11_03 | UPL | Settle UPL | 4 | D4R16 | Lend010_Settle UPL.docx | 2018-11-15 | 2018-11-16 | KhoaND | Done
D4 | 10_09 | Overdraft | Overview | 4 | D4R15 | Main001_My Finance.doc | 2018-11-19 | 2018-11-21 | KhoaND | Done
| 10_04 | Overdraft | Scenario: increase limits | 4 | D4R15 | Lend004_Increase Secured Overdraft.docx | 2018-11-20 | 2018-11-28 | Ngoc | Done
D4 | 10_02 | Overdraft | Open secure overdraft | 4 | D4R15 | Lend002_Open Secured Overdraft.docx | 2018-11-20 | 2018-12-03 | Thanh | Done
D4 | 10_05 | Overdraft | Overdraft details | 4 | D4R15 | Lend005_Overdraft Detail.docx | 2018-11-22 | 2018-11-26 | KhoaND | Done
D4 | 10_07 | Overdraft | Settle unsecured overdraft account | 4 | D4R15 | Lend006_Settle Overdraft.docx | 2018-11-27 | 2018-12-05 | KhoaND | Done
D4 | 10_01 | Overdraft | Overdraft account | 4 | D4R15 | Lend005_Overdraft Detail.docx | 2018-11-29 | 2018-12-03 | Ngoc | Done |  |  |  | BA: LanNTM (lanntm@vpbank.com.vn, 0977206555) PO: TrangNT122 (trangnt122@vpbank.com.vn, 0984049609)
D4 | 10_04 | Overdraft | Increase Secure OD | 4 | D4R15 | Lend004_Increase Secured Overdraft.docx | 2018-12-04 | 2018-12-18 | Ngoc | Cancelled |  |  | https://jira.vpbank.com.vn/browse/MOB-94
D4 | 10_03 | Overdraft | Open unsecure overdraft | 4 | D4R15 | Lend003_Open Unsecured Overdraft.docx | 2018-12-04 | 2018-12-17 | Thanh | Done
D4 | 10_06 | Overdraft | Settlle secure ovedraft account | 4 | D4R15 | Lend006_Settle Overdraft.docx | 2018-12-06 | 2018-12-18 | KhoaND | Done
D1 | 10_08 | Overdraft | Topup OD | 4 | D4R14 | Lend012_Topup OD.docx | 2018-12-07 | 2018-12-18 | DucLM | Postponed
D4 | 09_09 | Saving | Manage Saving | 4 | D6R17 | Savi008_Manage saving account.docx | 2018-12-11 | 2018-12-25 | Ngoc | WIP
D4 | 09_03 | Saving | Open saving | 4 | D6R17 | Savi001_Open saving.docx | 2018-12-18 | 2018-12-26 | Thanh | Open
D4 | 09_05 | Saving | Saving details | 4 | D6R17 | Savi008_Manage saving account.docx | 2018-12-19 | 2019-01-04 | DucLM | Done
D4 | 09_07 | Saving | Open Smart Combo (Saving + Secured OD) | 4 | D6R17 | Savi003_Open Smart Combo.docx | 2018-01-08 | 2019-01-16 | Thanh | WIP |  |  | https://vpb.sharepoint.com/:w:/s/uiuxproject/EfJlSsD_NCVNnIpWzFVtZIcBVIuDL6eNmPle3FCE59LeAQ?e=9gmVNu
D4 | 09_08 | Saving | Transfer to Easy Saving Account | 4 | D6R17 | Savi008_Manage saving account.docx | 2018-12-18 | 2018-12-28 | KhoaND | Open
D4 | 09_04 | Saving | Settle online saving | 4 | D6R17 | Savi002_Settle Saving.docx | 2018-12-27 | 2019-01-07 | Thanh | Open |  |  | https://jira.vpbank.com.vn/browse/MOB-93
D4 | 09_04_01 | Saving | Settle Smart Combo | 4 | D6R17 | Savi002_Settle Saving.docx | 2019-01-17 | 2019-01-25 | Thanh | Open |  |  | https://vpb.sharepoint.com/:w:/s/uiuxproject/EUJLGf_fRwxEhQChyxUeaowBETZb6Y0H5EOcj3XNyV04_A?e=nnRSPd
D4 | 09_06 | Saving | Rename Saving Account | 4 | D6R17 | Savi008_Manage saving account.docx | 2019-01-07 | 2019-01-09 | DucLM | WIP |  |  | https://jira.vpbank.com.vn/browse/MOB-253
D4 | 09_10 | Saving | Change Settle method | 4 | D6R17 | Savi008_Manage saving account.docx | 2019-01-10 | 2019-01-16 | DucLM | Done
D4 | 12_01 | Loan | Loan account | 4 | D4R16 | Lend013b_Loan Detail.docx | 2019-12-03 | 2019-12-06 | DucLM | Postponed
D4 | 12_04 | Loan | Loan detail | 4 | D4R16 | Lend013b_Loan Detail.docx | 2019-12-04 | 2019-12-10 | Ngoc | Done
D4 | 12_02 | Loan | Loan history | 4 | D4R16 | Lend013b_Loan Detail.docx | 27.11.2018 | 29.11.2018 | KhoaND | Cancelled
D4 | 12_03 | Loan | Scenario: Open loan | 4 | D4R16 | Lend008_Open UPL.docx
|  | Overdraft | Scenario: Request Overdraft
|  | Overdraft | Overdraft
| 10_06 | Overdraft | Scenario: settle overdraft | 4 | D4R15 | Lend006_Settle Overdraft.docx |  |  | KhoaND | Cancelled
D1 | 08_01 | Scheduled Payment | Scheduled Payment | 6 | D2R9 |  | Planning | Planning | BachLD | Open
D1 | 08_02 | Scheduled Payment | Scheduled Payment | 6 | D2R9 |  | Planning | Planning | BachLD | Open
D1 | 08_03 | Scheduled Payment | Scheduled Payment | 6 | D2R9 |  | Planning | Planning | BachLD | Open
D1 | 08_04 | Scheduled Payment | Scheduled Payment | 6 | D2R9 |  | Planning | Planning | BachLD | Open
D5 | 22_01 | Loyalty | Enquiry points (iCash) | 6 | D6R18 | Main008_Loyalty.docx | Planning | Planning | CuongNH25 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-1676
D5 | 22_02 | Loyalty | Redeem a gift | 6 | D6R18 | Main008_Loyalty.docx | Planning | Planning | CuongNH25 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-1676
D5 | 22_03 | Loyalty | Monitor the order | 6 | D6R18 | Main008_Loyalty.docx | Planning | Planning | CuongNH25 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-1676
D5 | 22_04 | Loyalty | Loyalty info | 6 | D6R18 | Main008_Loyalty.docx | Planning | Planning | CuongNH25 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-1676
D5 | 22_05 | Loyalty | Gift store | 6 | D6R18 | Main008_Loyalty.docx | Planning | Planning | CuongNH25 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-1676
D1 | 15_02_08 | More | Private information | 4 | D4R14 | Main006_More.docx | Planning | Planning | CuongNH25 | Open |  |  | Đã có service hiển thị thông tin
D1 | 15_02_09 | More | Scenario: edit profile | 4 | D4R14 | Main006_More.docx | Planning | Planning | Qulix | Open |  |  | Change avatar only per device
D5 | 15_04 | More | Notification list | 6 | D6R17 | Main006_More.docx | Planning | Planning | UIUX | Open |  |  | CMS thực hiện
D1 | 15_01 | More | Settings \ Touch ID & short PIN | 6 | D2R6 | Main006_More.docx | Planning | Planning | HaNV9 | Open
D1 | 15_02_07 | More | Settings \ Enable/Disable short PIN | 4 | D4R14 | Main006_More.docx | Planning | Planning | Qulix | Open |  |  | No APIs required
D4 | 15_05 | More | Saving interest rate | 4 | D4R14 | Main006_More.docx | Planning | Planning | CuongNH25 | Open |  |  | ?
D5 | 16_02 | More | ATM&Branches \ Route | 6 | D6R19 | Main006_More.docx | Planning | Planning | Qulix | Open |  |  | Dùng app bên thứ 3
D5 | 16_03 | More | ATM&Branches \ Filter | 6 | D6R19 | Main006_More.docx | Planning | Planning | CuongNH25 | Open |  |  | Hỏi lại Phát triển mạng lưới về CDN
D5 | 16_04 | More | ATM&Branches \ View list | 6 | D6R19 | Main006_More.docx | Planning | Planning | Qulix | Open |  |  | Client sử lý thêm 1 view
D5 | 16_05 | More | ATM&Branches \ View on map | 6 | D6R19 | Main006_More.docx | Planning | Planning | Qulix | Open |  |  | Client sẽ làm
D5 | 15_06 | More | FAQ | 4 | D6R18 | Main006_More.docx | Planning | Planning | Qulix | Open |  |  | UIUX - CMS quản lý
D5 | 23_01 | More | E-Wallet \ Register and map e-wallet | 6 | D6R19 | Main006_More.docx | Planning | Planning | BinhNT37 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-3297
D5 | 23_02 | More | E-Wallet \ Top up to e-wallet | 6 | D6R19 | Main006_More.docx | Planning | Planning | BinhNT37 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-3297
D5 | 23_03 | More | E-Wallet \ Unmap e-wallet | 6 | D6R19 | Main006_More.docx | Planning | Planning | BinhNT37 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-3297
D5 | 23_04 | More | E-Wallet \ MOMO | 6 | D6R19 | Main006_More.docx | Planning | Planning | BinhNT37 | Open |  |  | https://jira.vpbank.com.vn/browse/EBK-3297
D5 | 17_01 | Currency exchange | Currency exchange | 6 | D6R18 | Main006_More.docx | Planning | Planning | VanNTH10 | Open |  |  | ?
D1 | 02_02 | Authorization | Create account | Pp | D2R8 |  |  |  |  | Postponed |  |  | Postpone ( don’t have backend CRQ1/2019)
D1 | 02_01 | Authorization | Become VPBank Client | Pp | D6R18 |  |  |  |  | Postponed |  |  | Postpone ( don’t have backend CRQ1/2019)
D1 | 07_06_02 | Payment | QR code payment from search page | Pp | D6R17 |  |  |  |  | Postponed
D1 | 04_05 | Card | Reissue card | Bl | [5 empty] | Postponed |  |  | Block ( don’t have backend and on going build product procedure for Approved CRQ1/2019)
D1 | 04_17 | Card | Cash withdraw from credit card. | Bl | [5 empty] | Postponed |  |  | Block ( don’t have backend and on going build product procedure for Approved CRQ1/2019)
| 04_13 | Card | Đăng ký mở thẻ tín dụng (Credit open new credit cards) | [6 empty] | WIP |  |  | https://jira.vpbank.com.vn/browse/MOB-91
D4 | 04_15 | Card | Card Installment (Đăng ký vay trả góp) | 1 | D4R16 |  |  | 29.10.2018 |  | WIP |  |  |  | Card024_Card Installment.doc
D4 | 04_16 | Card | Payment and installment registration (TT và đăng ký trả góp) | 2 | D4R16 |  |  | N/A |  | Open |  |  |  | Card024_Card Installment.doc
D5 | 03_04 | Main | Promotion | 3 | D6R18 |  |  | 19.10.2018 |  | Done |  |  |  | Main007_Promotion.docx
Note on D69: FW: vpbank.ocb.a13: Current project status
Note on D70: FW: vpbank.ocb.a13: Current project status