## Sheet1
Module | Feature | Author | Delivery | Delivery date | File Description API | List Services | Changed | As-is APIs' Finished Date | Status | Develop | Start date Dev | End date dev
Overdraft | Scenario: increase limits | Ngocnv |  |  | Increase limit.docx | GetQueryOverdraft | Modify |  | Postponed | ngocnv | 2019-01-08 | 2019-01-11
UPL | View detail UPL | KhoaND | 8 | 2018-11-16 | View detail UPL.docx | - Accounts Service |  |  | Done |  |  |  | Service Modify: | 18 | Modify
Loan | Loan detail | Ngocnv |  |  | Loan detail.docx | LoanAccounts Service | Modify |  | Postponed | ngocnv | 2019-01-21 | 2019-01-24
UPL | View detail UPL | KhoaND |  |  | View detail UPL.docx | - LoanAccounts Service | [6 empty] | Service NoChange: | 53
UPL | Open UPL | KhoaND | 5 | 2018-11-16 | Open UPL.docx | - Overdrafts?action=init Service |  |  | Done |  |  |  | COUNT PostPone: | 6 | Postponed
UPL | Open UPL | KhoaND |  |  | Open UPL.docx | - GetAccounts Service
UPL | Open UPL | KhoaND |  |  | Open UPL.docx | - GetAccounts drawAccount Service
Overdraft | Open Secured Overdraft | ThanhNV |  |  | Open Secured Overdraft.docx | GetOnlineSavingAccountsList Service | Modify |  | Postponed | ngocnv | 2018-12-18 | 2018-12-21
UPL | Open UPL | KhoaND |  |  | Open UPL.docx | - GetIntroducerInfo Service
Overdraft | Open Secured Overdraft | ThanhNV |  |  | Open Secured Overdraft.docx | Overdrafts?action=verify Service | Modify |  | Done | khoand | 2018-12-18 | 2018-12-20
UPL | Open UPL | KhoaND |  |  | Open UPL.docx | - Authentication Service |  |  |  |  | 2019-01-10 | 2019-01-14
Overdraft | Open Secured Overdraft | ThanhNV |  |  | Open Secured Overdraft.docx | Overdrafts?action=confirm Service | Modify |  | Done | khoand | 2018-12-21 | 2018-12-25
UPL | Settle UPL | KhoaND | 5 | 2018-11-16 | Settle UPL.docx | - Overdrafts?action=init Service |  |  | Done |  | 2018-12-21 | 2018-12-25
UPL | Settle UPL | KhoaND |  |  | Settle UPL.docx | - GetBankDate Service |  |  |  |  | 2018-12-26 | 2018-12-28
UPL | Settle UPL | KhoaND |  |  | Settle UPL.docx | - GetOverDraftAccountForSettlement Service |  |  |  |  | 2019-01-02 | 2019-01-04
UPL | Settle UPL | KhoaND |  |  | Settle UPL.docx | - GetAccounts Service
UPL | Settle UPL | KhoaND |  |  | Settle UPL.docx | - GetLoanByID Service
UPL | Settle UPL | KhoaND |  |  | Settle UPL.docx | - Overdrafts?action=verify Service
UPL | Settle UPL | KhoaND |  |  | Settle UPL.docx | - SecureUsers?action=authenticateMFA Service
UPL | Settle UPL | KhoaND |  |  | Settle UPL.docx | - Overdrafts?action=confirm Service
Overdraft | Settlle secure ovedraft account | KhoaND |  |  | Settlle secure ovedraft account.docx | Overdrafts?action=verify Service | Modify |  | Cancelled | khoand | 2019-01-04 | 2019-01-08
Overdraft | Settle unsecured overdraft account | KhoaND | 7 | 2018-12-05 | Settlle Unsecure ovedraft account.docx | - Overdrafts?action=init Service |  |  | Done
Overdraft | Settle unsecured overdraft account | KhoaND |  |  | Settlle Unsecure ovedraft account.docx | - GetBankDate Service
Overdraft | Settle unsecured overdraft account | KhoaND |  |  | Settlle Unsecure ovedraft account.docx | - GetOverDraftAccountForSettlement Service
Overdraft | Open Unsecured Overdraft | ThanhNV |  |  | Open Unsecured Overdraft.docx | Overdrafts?action=verify Service | Modify |  | WIP | khoand | 2019-01-09 | 2019-01-10
Overdraft | Settle unsecured overdraft account | KhoaND |  |  | Settlle Unsecure ovedraft account.docx | - SecureUsers?action=authenticateMFA Service |  |  |  |  | 2019-01-15 | 2019-01-17
UPL | Open UPL | KhoaND |  |  | Open UPL.docx | GetInsuranceFeeInfo Service | Modify |  | Postponed | ngocnv | 2018-12-22 | 2018-12-28
Overdraft | Settlle secure ovedraft account | KhoaND | 7 | 2018-12-14 | Settlle secure ovedraft account.docx | - Overdrafts?action=init Service |  |  | Done |  | 2018-12-21 | 2018-12-25
Overdraft | Settlle secure ovedraft account | KhoaND |  |  | Settlle secure ovedraft account.docx | - GetBankDate Service |  |  |  |  | 2018-12-26 | 2018-12-28
Overdraft | Settlle secure ovedraft account | KhoaND |  |  | Settlle secure ovedraft account.docx | - GetOverDraftAccountForSettlement Service |  |  |  |  | 2019-01-02 | 2019-01-04
Overdraft | Open Unsecured Overdraft | ThanhNV |  |  | Open Unsecured Overdraft.docx | Overdrafts?action=confirm Service | Modify |  |  | khoand | 2019-01-11 | 2019-01-14
Overdraft | Settlle secure ovedraft account | KhoaND |  |  | Settlle secure ovedraft account.docx | - SecureUsers?action=authenticateMFA Service |  |  |  |  | 2019-01-15 | 2019-01-17
Overdraft | Settlle secure ovedraft account | KhoaND |  |  | Settlle secure ovedraft account.docx | - Overdrafts?action=confirm Service |  |  |  |  | 2019-01-18 | 2019-01-22
Saving | Saving Info | ThanhNV | 5 | 16/11/2018 | Saving Info.docx | Accounts Service |  |  | Done |  | 2019-02-23 | 2019-01-25
Overdraft | Settle unsecured overdraft account | KhoaND |  |  | Settlle Unsecure ovedraft account.docx | Overdrafts?action=verify Service | Modify |  |  | khoand | 2019-01-15 | 2019-01-16
Overdraft | Overdraft account | Ngocnv |  |  | Overdraft account.docx | Asset Account Transactions Service | Modify |  | Done | duclm | 2018-12-24 | 2018-12-28
Overdraft | Open Secured Overdraft | ThanhNV | 10 | 2018-03-12 | Open Secured Overdraft.docx | Overdrafts?action=init Service |  |  | Done
Overdraft | Overdraft details | KhoaND | 3 | 2018-11-26 | Overdraft details.docx | GetOverdraftDetailById Service | New |  | Done | duclm | 2018-12-24 | 2018-12-28
Overdraft | Open Secured Overdraft | ThanhNV |  |  | Open Secured Overdraft.docx | GetRequestOverdraftAccountsList Service
Overdraft | Open Secured Overdraft | ThanhNV |  |  | Open Secured Overdraft.docx | GetBankDate Service
Overdraft | Open Secured Overdraft | ThanhNV |  |  | Open Secured Overdraft.docx | GetMaturityDate Service
Overdraft | Open Secured Overdraft | ThanhNV |  |  | Open Secured Overdraft.docx | GetCollectionAccountsList Service
Overdraft | Overview | KhoaND | 3 | 2018-11-21 | Overdraft Overview.docx | LoanAccounts Service | Modify |  | Done | ngocnv | 2019-01-14 | 2019-01-18 | Services Done: | 51
Overdraft | Open Secured Overdraft | ThanhNV |  |  | Open Secured Overdraft.docx | SecureUsers Service |  |  |  |  | 2019-01-15 | 2019-01-17
Overdraft | Open Unsecured Overdraft | ThanhNV | 10 | 17/12/2018 | Open Unsecured Overdraft.docx | Overdrafts?action=init Service |  |  | Done |  | 2018-12-21 | 2018-12-25
Overdraft | Open Unsecured Overdraft | ThanhNV |  |  | Open Unsecured Overdraft.docx | GetRequestOverdraftAccountsList Service |  |  |  |  | 2018-12-26 | 2018-12-28
Overdraft | Open Unsecured Overdraft | ThanhNV |  |  | Open Unsecured Overdraft.docx | GetBankDate Service |  |  |  |  | 2019-01-02 | 2019-01-04
Overdraft | Open Unsecured Overdraft | ThanhNV |  |  | Open Unsecured Overdraft.docx | GetCollectionAccountsList Service
UPL | View detail UPL | KhoaND |  |  | View detail UPL.docx | GetAccountDetailsByID Service | Modify |  | Postponed | duclm | 2019-01-02 | 2019-01-04
Overdraft | Open Unsecured Overdraft | ThanhNV |  |  | Open Unsecured Overdraft.docx | SecureUsers Service |  |  |  |  | 2019-01-15 | 2019-01-17
Saving | Saving Info | ThanhNV |  |  | Saving Info.docx | AssetAccounts Service | Modify |  | Open | duclm | 2019-01-04 | 2019-01-08
Overdraft | Settle unsecured overdraft account | KhoaND |  |  | Settlle Unsecure ovedraft account.docx | Overdrafts?action=confirm Service | Modify |  |  | khoand | 2019-01-17 | 2019-01-18
Saving | Change settle method | DucLM | 2 | 2018-12-14 | Saving_ChangeSettleMethod.docx | GetOnlineSavingDetail |  |  | Done |  | 2018-12-26 | 2018-12-28
Saving | Change settle method | DucLM |  |  | Saving_ChangeSettleMethod.docx | GetSettleToAccountsList |  |  |  |  | 2019-01-02 | 2019-01-04
Saving | Change settle method | DucLM |  |  | Saving_ChangeSettleMethod.docx | GetMaturityMethod
Saving | Change settle method | DucLM |  |  | Saving_ChangeSettleMethod.docx | OnlineSavings?action=verify
Saving | Change settle method | DucLM |  |  | Saving_ChangeSettleMethod.docx | OnlineSavings?action=confirm
Saving | Change settle method | DucLM |  |  | Saving_ChangeSettleMethod.docx | SecureUsers?action=authenticateMFA
Lending | Topup OD | DucLM |  |  | Lending_TopupOD.docx |  |  |  | Postponed
Overdraft | Scenario: increase limits | Ngocnv | 8 | 2018-11-28 | Increase limit.docx | - Accounts Service |  |  | Done
Overdraft | Scenario: increase limits | Ngocnv |  |  | Increase limit.docx | - Overdrafts?action=init Service
UPL | Open UPL | KhoaND |  |  | Open UPL.docx | Overdrafts?action=confirm Service | Modify |  |  | khoand | 2019-01-21 | 2019-01-22
Overdraft | Scenario: increase limits | Ngocnv |  |  | Increase limit.docx | - GetOnlineSavingAccountsList Service
Overdraft | Scenario: increase limits | Ngocnv |  |  | Increase limit.docx | - Overdrafts?action=verify Service
Overdraft | Scenario: increase limits | Ngocnv |  |  | Increase limit.docx | - SecureUsers?action=authenticateMFA Service
Overdraft | Scenario: increase limits | Ngocnv |  |  | Increase limit.docx | - Overdrafts?action=confirm Service
Overdraft | Overdraft account | Ngocnv | 5 | 2018-12-03 | Overdraft account.docx | - Accounts Service |  |  | Done
Overdraft | Overdraft account | Ngocnv |  |  | Overdraft account.docx | - GetAccountDetailById Service
Overdraft | Overdraft account | Ngocnv |  |  | Overdraft account.docx | - Get Debit Card Attached with Account Service
UPL | Open UPL | KhoaND |  |  | Open UPL.docx | Overdrafts?action=verify Service | Modify |  |  | khoand | 2019-01-23 | 2019-02-24
Loan | Loan detail | Ngocnv | 6 | 2018-12-10 | Loan detail.docx | - Accounts Service |  |  | Done
Loan | Loan detail | Ngocnv |  |  | Loan detail.docx | - GetAccountDetailById Service
Saving | Saving details | DucLM | 1 | 2018-12-04 | Saving_Detail.docx | GetAccountDetailsByID | Modify |  | Done | duclm | 2019-01-04 | 2019-01-08 | Service New: | 0 | New
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | OnlineSavings?action=init
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | OnlineSavingAccountTypes Service
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | GetBankDate Service
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | GetAccountsByAccountTypeID Service
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | GetMaturityMethod Service
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | GetTerms Service
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | GetOnlineSavingRatesBySearchCriteria Service
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | GetIntroducerInfo Service
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | OnlineSavings?action=verify
Saving | Open saving | ThanhNV |  |  | Open Saving.docx | OnlineSavings?action=confirm Service
Saving | Manage Saving | Ngocnv |  |  | Saving Manage Account - Saving Detail.docx | Accounts Service
Saving | Manage Saving | Ngocnv |  |  | Saving Manage Account - Saving Detail.docx | GetAccountDetailById Service | Modify |  |  | duclm | 2019-01-04 | 2019-01-08
Saving | Manage Saving | Ngocnv |  |  | Saving Manage Account - Saving Detail.docx | AssetAccounts Service:
Saving | Settle online saving | ThanhNV |  |  | Settle online saving | OnlineSavings?action=init Service
Saving | Settle online saving | ThanhNV |  |  | Settle online saving | GetOnlineSavingAccountsList Service
Saving | Settle online saving | ThanhNV |  |  | Settle online saving | GetLockAmounts Service
Saving | Settle online saving | ThanhNV |  |  | Settle online saving | GetSettleToAccountsList Service
Saving | Settle online saving | ThanhNV |  |  | Settle online saving | OnlineSavings?action=verify Service | Modify |  | Open | ngocnv | 2019-01-07 | 2019-01-11
Saving | Settle online saving | ThanhNV |  |  | Settle online saving | Authentication Service
Saving | Settle online saving | ThanhNV |  |  | Settle online saving | OnlineSavings?action=confirm Service
Saving | Settle online saving | ThanhNV |  |  | Settle online saving | GetAccountDetailsByID Service | Modify |  | Open | ngocnv | 2019-01-07 | 2019-01-11
Note on D1: Desktop: số ngày hoàn thành
Note on I1: Desktop: ngày hoàn thành API

## Sheet3
|  |  |  | start | End
Saving_Detail.docx | GetAccountDetailsByID | Modify | duclm | 2018-12-18 | 2018-12-24
Saving Info.docx | AssetAccountsByTime Service | New | duclm | 2018-12-25 | 2018-12-28
Saving Info.docx | AssetAccounts Service | Modify | duclm | 2019-01-02 | 2019-02-07
Overdraft account.docx | Asset Account Transactions Service | Modify | duclm | 2019-01-08 | 2019-01-11
View detail UPL.docx | GetAccountDetailsByID Service | Modify | duclm | 2019-01-14 | 2019-01-18
Open UPL.docx | GetInsuranceFeeInfo Service | Modify | ngocnv | 2018-12-18 | 2018-12-24
Open Secured Overdraft.docx | GetOnlineSavingAccountsList Service | Modify | ngocnv | 2018-12-25 | 2018-12-28 | duc | 2019-01-18 | 5
Overdraft details.docx | GetOverdraftDetailById Service | New | ngocnv | 2019-01-02 | 2019-02-07 | khoa | 2019-01-25 | 9
Increase limit.docx | GetQueryOverdraft | Modify | ngocnv | 2019-01-08 | 2019-01-11 | ngoc | 2019-01-24 | 6
Overdraft Overview.docx | LoanAccounts Service | Modify | ngocnv | 2019-01-14 | 2019-01-18
Loan detail.docx | LoanAccounts Service | Modify | ngocnv | 2019-01-21 | 2019-01-24
Settlle Unsecure ovedraft account.docx | Overdrafts?action=confirm Service | Modify | khoand | 2018-12-18 | 2018-12-20
Open Secured Overdraft.docx | Overdrafts?action=confirm Service | Modify | khoand | 2018-12-21 | 2018-12-25
Open Unsecured Overdraft.docx | Overdrafts?action=confirm Service | Modify | khoand | 2018-12-26 | 2018-12-28
Open UPL.docx | Overdrafts?action=confirm Service | Modify | khoand | 2019-01-02 | 2019-01-04
Open UPL.docx | Overdrafts?action=verify Service | Modify | khoand | 2019-01-07 | 2019-01-09
Settlle Unsecure ovedraft account.docx | Overdrafts?action=verify Service | Modify | khoand | 2019-01-10 | 2019-01-14
Settlle secure ovedraft account.docx | Overdrafts?action=verify Service | Modify | khoand | 2019-01-15 | 2019-01-17
Open Secured Overdraft.docx | Overdrafts?action=verify Service | Modify | khoand | 2019-01-18 | 2019-01-22
Open Unsecured Overdraft.docx | Overdrafts?action=verify Service | Modify | khoand | 2019-02-23 | 2019-01-25